## Slide 1
When we need Project Management
33
www.qmsiso.com
1

## Slide 2
Project Initiation Stage
Project Lifecycle Model
Project Management Roles
Documenting Project Objective
Final Result Description
Determining Project Milestones
Determining Preliminary Resources
www.qmsiso.com
2

## Slide 3
Most of the Projects are initiated based on the following reasons (for Industrial Sector):
  New Installation
  New Product Designing (Prototype)
  New Process Designing and Installation
  Enhancement of existing Process or Product
  Development of New Site
  Up gradation : Equipment & Machinery
www.qmsiso.com
3

## Slide 4
Most probable reasons behind such initiations are to meet Customer’s (Stakeholders) new requirements OR to compete with market competitors OR to enhance productivity
But an initiation is only considered “Project Initiation” when the idea has been documented and presented to approving
CouarseuCodteh: PoM-0r2ities
www.qmsiso.com
4

## Slide 5
An Initiating Officer documents the Project Requirement
The document gives the following details:
  Project Requirement
  Advantages
  Its effects on Existing Processes
  Final Objective (Expected Result)
  Projected Timeline
www.qmsiso.com

## Slide 6: Initiating Officer
Project Objective
Initiation
Documentation
Example:
K-8 Project
www.qmsiso.com

## Slide 7
On the basis of Project Initiation Document, approving authorities appoint a Project Manager (may call Proj. Dir. at times)
Project Manager’s role is to ensure:
  Requirement Analysis
  Project Scoping
  Project Phases and Milestones (Draft Model)
  Resource requirement
And this is just the beginning …
www.qmsiso.com

## Slide 8
Project Manager designs a model that represents Project’s Lifecycle
The lifecycle can be in form of a document, process flow or even a table chart
It should express general phases overview with deliverables to get to final objective of Project
It is also preferred to express timeline as well
www.qmsiso.com

## Slide 9
 | Planning Phase (6 weeks) | 
Resource Allocation | Project Scope & Plan | Roles & Tasking
 | Assessment Phase (8 weeks) | 
Cost Analysis & Budgeting | Comparisons | Risk Assessment
Implementation and Correction Phase (24 weeks) |  | 
Prototype Design | Development and QA | Change Management
 | Closure (4 weeks) | 
Final Prototype Delivery | Final Approval | Closing Documentation
www.qmsiso.com

## Slide 10
Based on the Project Lifecycle, Project Manager can chalk down Project Milestones
These short targets will ensure proper project progress
Based on their achievement, Project Progress can be monitored and reviewed
It is recommended to put Milestones in the end of each phase, so that their delivery can also express phase closing and a stepping stone for next phase
www.qmsiso.com

## Slide 11
A Milestone or Deliverable must express these characteristics:
  It should be a useful component of the Project
  It should contribute in achievement of Project Objective
  It should be supported with a document / report
Weak and unrelated deliverables will never give true picture of the Project Lifecycle
And they always disturb Project Scoping!
www.qmsiso.com

## Slide 12
Project Manager shall document these and on its basis shall identify scope of project
Project Scoping document is separate from this for ease of document management associated with Project Management
After approval of Project Initiation Document, Project Manager starts Project Scoping, a short but very important part of Project Management …
Mod 3
www.qmsiso.com